## Project plan
Extension Dynamics CRM / MS Power Platform
godiz ag |  | = Task was worked on during this 2 hour increment
Josiah Spilker | Monday |  | Tuesday | Wednesday | Thursday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday
2026-04-27 | 27.04.26 |  | 28.04.26 | 29.04.26 | 30.04.26 | 04.05.26 | 05.05.26 | 06.05.26 | 07.05.26 | 08.05.26 | 11.05.26
T0 : Documentation + Administration
T1 : Inform
T1.1 : Analyze Task Req.
T1.2 : Review Dynamics Setup
T1.3 : Grasp basic structure
T2 : Plan
T2.1 : Gantt Diagram
T2.2 : Create Use Case Diagram
T2.3 : Create Context Diagram
T2.4 : Create ERM Model
T2.5 : Define Requirements
T2.6 : Define Project Organisation & Roles
T2.7 : Realisation Concept
T2.8 : Test Plan/Cases
T3 : Decide
T3.1 : Architecture & Design Decisions
T3.2: PCF Structure
T3.3: Dataverse Entity & Data Model Design
T3.4: Merge & Deactivation Logic
T3.5: UI / UX Wireframe
T4 : Realise
T4.1 : Implement Dataverse Entities
T4.2 : Configure Model Driven App
T4.3 : Set Up PCF Project in app
T4.4 : Implement Data Fetching Layer
T4.5 : Implement Field Type Handlers
T4.6 : Implement Comparison UI
T4.7 : Implement Merge & Deactivation Logic
T4.8 : Seed Test Data
T4.9 : Final checks
T4.10 : Export Managed Solution
T5 : Control
T5.1 : Create / Execute Functional Test Cases
T5.2 : Robustness & Negative Testing
T5.3 : Bugfixing & Refinement
T6 : Evaluate
T6.1 : Write instruction manual
T6.2 : Write Reflection
T6.3 : Finalize Report
T6.4 : Plan vs. Actual Analysis
T6.5 : Project Handover & Review

## Temp Soll
Extension Dynamics CRM / MS Power Platform
godiz ag
Josiah Spilker |  | Monday |  | Tuesday | Wed. | Thursday |  | Monday | Tuesday | Wed. | Thursday | Friday |  |  | Monday
27.04.2026 / = <1h |  | 27.04.26 |  | 28.04.26 | 29.04.26 | 30.04.26 |  | 04.05.26 | 05.05.26 | 06.05.26 | 07.05.26 | 08.05.26 |  |  | 11.05.26
T0 : Documentation/Admin. 16h | 2h daily
T1 : Inform 3h | 4h
T1.1 : Analyze Task Req. | should
is
T1.2 : Review Dynamics Setup | should |  | /
is
T1.3 : Grasp basic structure | should |  | /
is
T2 : Plan 14h | 18h
T2.1 : Gantt Diagram | should
is
T2.2 : Create Use Case Diagram | should
is
T2.3 : Create Context Diagram | should
is
T2.4 : Create ERM Model | should
is
T2.5 : Define Requirements | should
is
T2.6 : Define Project Roles | should |  |  |  | /
is
T2.7 : Realisation Concept | should |  |  |  | /
is
T2.8 : Test Plan/Cases | should
is
T3 : Decide 5h | 6h
T3.1 : Architecture Decisions | should
is
T3.2: PCF Structure | should |  |  |  |  | /
is
T3.3: Dataverse Entity Design | should |  |  |  |  | /
is
T3.4: Merge/Deactivation Logic | should | [5 empty] | /
is
T3.5: UI / UX Wireframe | should | [5 empty] | /
is
T4 : Realise 18h | 28h
T4.1 : Implement Dataverse Entities | should
is
T4.2 : Configure Model Driven App | should
is
T4.3 : Set Up PCF Project in app | should
is
T4.4 : Implement Data Fetching Layer | should
is
T4.5 : Implement Field Type Handlers | should
is
T4.6 : Implement Comparison UI | should
is
T4.7 : Implement Merge Logic | should
is
T4.8 : Seed Test Data | should
is
T4.9 : Final checks | should
is
T4.10 : Export Managed Solution | should
is
T5 : Control 6h | 8h
T5.1 : Execute Test Cases | should
is
T5.2 : Robustness/Negative Testing | should
is
T5.3 : Bugfixing & Refinement | should
is
T6 : Evaluate 8h | 16h
T6.1 : Write instruction manual | should
is
T6.2 : Write Reflection | should
is
T6.3 : Finalize Report | should | [11 empty] | /
is
T6.4 : Plan vs. Actual Analysis | should | [11 empty] | / | /
is
T6.5 : Project Handover & Review | should | [12 empty] | /
is
T7 : Buffer 8h | 16h

## Project plan Should Is
Extension Dynamics CRM / MS Power Platform
godiz ag |  | / = 1h |  | Documentation + Administration is meant as an overarching task that is worked on simultaneously with other tasks.
Josiah Spilker |  | Monday |  |  |  | Tuesday | Wednesday | Thursday |  | Monday | Tuesday | Wednesday | Thursday | Friday |  |  | Monday
2026-04-27 |  | 27.04.26 |  |  |  | 28.04.26 | 29.04.26 | 30.04.26 |  | 04.05.26 | 05.05.26 | 06.05.26 | 07.05.26 | 08.05.26 |  |  | 11.05.26
T0 : Documentation + Administration | 2h daily
T1 : Inform | 4h
T1.1 : Analyze Task Req. | should
is
T1.2 : Review Dynamics Setup | should |  | /
| is |  | /
T1.3 : Grasp basic structure | should |  | /
| is |  | /
T2 : Plan | 18h
T2.1 : Gantt Diagram | should
| is |  |  | /
T2.2 : Create Use Case Diagram | should
| is |  |  | /
T2.3 : Create Context Diagram | should
| is |  |  |  | /
T2.4 : Create ERM Model | should
| is |  |  |  | /
T2.5 : Define Requirements | should
is
T2.6 : Define Project Organisation & Roles | should | [5 empty] | /
is
T2.7 : Realisation Concept | should | [5 empty] | /
is
T2.8 : Test Plan/Cases | should
is
T3 : Decide | 6h
T3.1 : Architecture & Design Decisions | should
is
T3.2: PCF Structure | should | [6 empty] | /
is
T3.3: Dataverse Entity & Data Model Design | should | [6 empty] | /
is
T3.4: Merge & Deactivation Logic | should | [7 empty] | /
is
T3.5: UI / UX Wireframe | should | [7 empty] | /
is
T4 : Realise | 28h
T4.1 : Implement Dataverse Entities | should
is
T4.2 : Configure Model Driven App | should
is
T4.3 : Set Up PCF Project in app | should
is
T4.4 : Implement Data Fetching Layer | should
is
T4.5 : Implement Field Type Handlers | should
is
T4.6 : Implement Comparison UI | should
is
T4.7 : Implement Merge & Deactivation Logic | should
is
T4.8 : Seed Test Data | should
is
T4.9 : Final checks | should
is
T4.10 : Export Managed Solution | should
is
T5 : Control | 8h
T5.1 : Create / Execute Functional Test Cases | should
is
T5.2 : Robustness & Negative Testing | should
is
T5.3 : Bugfixing & Refinement | should
is
T6 : Evaluate | 8h
T6.1 : Write instruction manual | should
is
T6.2 : Write Reflection | should
is
T6.3 : Finalize Report | should | [13 empty] | /
is
T6.4 : Plan vs. Actual Analysis | should | [13 empty] | / | /
is
T6.5 : Project Handover & Review | should | [14 empty] | /
is
T7 : Buffer 8h | 8h

## Small
Extension Dynamics CRM / MS Power Platform
godiz ag
Josiah Spilker | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Monday |  |  |  | Tuesday |  |  |  | Wednesday |  |  |  | Thursday |  |  |  | Friday |  |  |  | Monday
2026-04-27 | 27.04.26 |  |  |  | 28.04.26 |  |  |  | 29.04.26 |  |  |  | 30.04.26 |  |  |  | 04.05.26 |  |  |  | 05.05.26 |  |  |  | 06.05.26 |  |  |  | 07.05.26 |  |  |  | 08.05.26 |  |  |  | 11.05.26
Task | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00 | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00 | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00 | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00 | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00 | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00 | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00 | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00 | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00 | 8:00-10:00 | 10:00-12:00 | 13:00-15:00 | 15:00-17:00
T0 : Documentation
T1 : Inform
T1.1 : Analyze Task Req.
T1.2 : Review Dynamics Setup
T1.3 : Grasp basic structure
T2 : Plan
T2.1 : Gantt Diagram
T2.2 : Create UML Diagrams
T2.3 : Create Context Diagram
T2.4 : Create ERM Model
T2.5 : Test Plan/Cases
T3 : Decide
T3.1 : Architecture & Design Decisions
T4 : Realise
T4.1 : Implement Dataverse Entities
T4.2 : Implement Business Logic
T4.3 : Configure Model Driven App
T4.4 : Develop Warning Cloud Flow
T4.5 : Develop Auto-close Cloud Flow
T4.6 : Create Weekly Cost Overview Flow
T4.7 : Final checks
T4.8 : Export Managed Solution
T5 : Control
T5.1 : Create / Execute Functional Test Cases
T5.2 : Robustness & Negative Testing
T5.2 : Bugfixing & Refinement
T6 : Evaluate
T6.1 : Write Reflection etc.
T6.2 : Finalize Report
T6.3 : Plan vs. Actual Analysis
T6.4 : Project Handover & Review
OLD
[25 empty] | Legend: |  | Complete |  | Planned |  | Absent |  | Overtime

## Mini
Task | Estimate (Hours) | Total (Hours) | Deviation (Hours) | Justification
T0 : Documentation | 15.00 h | 18.25 h | + 3.25 h | Underestimated effort for final report compilation, formatting, and Gantt chart integration.
T1 : Inform | 4.75 h | 3.25 h | - 1.50 h | Information gathering was more efficient than anticipated due to prior knowledge.
T2 : Plan | 11.00 h | 7.50 h | - 3.50 h | Planning was completed faster than scheduled; standard templates accelerated the process.
T3 : Decide | 1.00 h | 0.50 h | - 0.50 h | Decision-making was straightforward with no major architectural conflicts.
T4 : Realise | 22.00 h | 10.75 h | - 11.25 h | Slight deviation. The "Low-Code" nature of Dataverse allowed for extremely rapid implementation of entities and flows
T5 : Control | 10.00 h | 4.50 h | - 5.50 h | Testing proceeded quickly as no major bugs required extensive reworking.
T6 : Evaluate | 8.00 h | 6.50 h | - 1.50 h | Evaluation was completed within the scheduled timeframe.
Total | 71.75 h | 51.25 h | - 20.50 h | Project completed significantly before schedule.
OLD

## Info
EINFACHES GANTT-DIAGRAMM von Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Über diese Vorlage
Diese Vorlage bietet eine einfache Möglichkeit, ein Gantt-Diagramm zu erstellen, um Ihr Projekt zu visualisieren und seine Nachverfolgung zu erleichtern. Geben Sie einfach Ihre Aufgaben sowie das Start- und Enddatum ein; es sind keine Formeln erforderlich. Die Balken im Gantt-Diagramm stellen die Dauer der Aufgabe dar und werden mithilfe bedingtes Formatierungen angezeigt. Fügen Sie neue Aufgaben ein, indem Sie neue Zeilen einfügen.
Leitfaden für die Sprachausgabe
Diese Arbeitsmappe enthält 2 Arbeitsblätter. Arbeitszeittabelle Info Die Anweisungen für jedes Arbeitsblatt befinden sich in Spalte A ab Zelle A1 der einzelnen Arbeitsblätter. Sie sind in verborgenem Text geschrieben. Jeder Schritt führt Sie durch die Informationen in der betreffenden Zeile. Jeder nachfolgende Schritt fährt in den Zellen A2, A3 usw. fort, sofern nicht ausdrücklich anders angegeben. Beispielsweise kann der Anweisungstext etwa für den nächsten Schritt "Mit Zelle 6 fortfahren" besagen. Dieser verborgene Text wird nicht gedruckt. Um diese Anweisungen aus dem Arbeitsblatt zu entfernen, löschen Sie einfach Spalte A.
Weitere Hilfe
Klicken Sie auf den Link unten, um zu vertex42.com zu gehen und mehr über die Verwendung dieser Vorlage zu erfahren, z. B. wie Tage und Arbeitstage berechnet werden, wie Aufgabenabhängigkeiten erstellt werden, wie die Farben der Balken geändert werden, wie eine Bildlaufleiste hinzugefügt wird, um die Anzeigewoche einfacher zu ändern, wie der in dem Diagramm angezeigte Datumsbereich geändert wird usw.
Verwenden des einfachen Gantt-Diagramms
Weitere Projektmanagementvorlagen
Rufen Sie Vertex42.com auf, um weitere Projektmanagementvorlagen herunterzuladen, einschließlich unterschiedlicher Typen von Projektplänen, Gantt-Diagramme, Aufgabenlisten usw.
Projektmanagementvorlagen
Informationen zu Vertex42
Vertex42.com bietet mehr als 300 professionell entworfene Tabellenkalkulationsvorlagen für die Nutzung im Geschäft, zu Hause und in Bildungseinrichtungen – die meisten können Sie kostenlos herunterladen. Die Sammlung beinhaltet eine Vielzahl von Kalendern, Planern und Zeitplänen sowie Tabellen für die private Finanzkalkulation zur Erstellung von Budgets, Reduzierung von Belastungen und Amortisation von Darlehen.
Unternehmen werden bei Rechnungen, Arbeitszeittabellen, Bestandstrackern, Geschäftsberichten und Vorlagen für die Projektplanung fündig. Lehrer und Schüler finden Ressourcen wie Stundenpläne, Klassenbücher und Teilnahmebögen. Organisieren Sie Ihr Familienleben mit Speiseplänen, Checklisten und Übungsprotokollen. Jede Vorlage wurde gründlich recherchiert, verfeinert und im Lauf der Zeit anhand des Feedbacks von Tausenden von Benutzern verbessert.